## Deliverables by Month
CEU Matrix — SEO Deliverables by Month
$4,500/mo · 4-Month Commitment · EmberTribe × CEU Matrix
# | Category | Deliverable | Description | Owner | Status
MONTH 1 — Foundation
1 | SEO Foundation | Technical SEO Audit | Full site crawl: broken links, missing meta, duplicate H1s, thin content, indexation issues, site speed. Deliverable: written audit report. | EmberTribe
2 | SEO Foundation | Keyword Research & Mapping | State-by-state certification keyword matrix. Maps target keywords to existing and planned pages. Includes volume, difficulty, intent. | EmberTribe
3 | SEO Foundation | Content Strategy Document | Full-funnel content plan: pillar pages, cluster topics, 4-month blog calendar, state page build order. | EmberTribe
4 | SEO Foundation | Competitor Analysis Report | Keyword gap, backlink gap, content gap vs. CASR + 4 other competitors. Identifies quick-win opportunities. | EmberTribe
5 | SEO Foundation | Backlink Gap Report | Identifies every domain linking to CASR/CE4Less/Sober College that doesn't link to CEU Matrix. Basis for Month 2+ outreach. | EmberTribe
6 | SEO Foundation | Ohio Hub Page Content Brief | Full content brief for the new Ohio informational hub: target keywords, H1/H2 structure, credential tables, FAQ targets, word count, internal link plan. | EmberTribe
7 | SEO Foundation | Reporting Dashboard Setup | Live keyword position tracking dashboard. Baseline rankings recorded for all target keywords before any work begins. | EmberTribe
8 | Content | 10 ClusterMagic Articles (or 3 Backlinks) | Month 1 bonus deliverable: either 10 SEO-optimized blog articles published OR 3 backlinks acquired — CEU Matrix's choice. | EmberTribe
9 | Reporting | Kickoff / Intake Call | Day 3 intake call. Align on state priority (Ohio first), review access setup, confirm content approval workflow. | Both
10 | Access Setup | GA4 + GSC Access | CEU Matrix grants GA4 viewer access and Google Search Console access to EmberTribe. | CEU Matrix
11 | Access Setup | WordPress + WooCommerce Admin | CEU Matrix provides secure WordPress admin login and WooCommerce access to EmberTribe. | CEU Matrix
12 | Access Setup | Brand Guidelines & State Approvals List | CEU Matrix provides brand guidelines, logo files, and full list of state board approvals held (for on-page citation). | CEU Matrix
MONTH 2 — Publish
13 | Content | 20 ClusterMagic Articles | 20 SEO-optimized blog articles. Human-edited, internally linked, alt-texted images. Topics from approved content calendar. | EmberTribe
14 | Backlinks | 6 Quality Backlinks | 6 backlinks acquired from relevant domains: state board directories, NAADAC-adjacent sites, certification listings, counselor orgs. | EmberTribe
15 | Technical | Canonical Tags — /course/ vs /product/ Duplicates | Add canonical tags to all 4 /course/ + /product/ credential pairs to consolidate authority into one URL per credential. | EmberTribe
16 | Technical | FAQPage JSON-LD — Ohio Hub | Implement FAQPage schema markup on the Ohio unified hub page. Targets featured snippets and People Also Ask placement. | EmberTribe
17 | Technical | FAQPage JSON-LD — CDCA Preliminary Page | Implement FAQPage schema on the new CDCA Preliminary credential page. | EmberTribe
18 | Technical | FAQPage JSON-LD — CDCA Renewable Page | Implement FAQPage schema on the new CDCA Renewable credential page. | EmberTribe
19 | Technical | BreadcrumbList Schema — Ohio Pages | Add BreadcrumbList JSON-LD to Ohio hub and all Ohio credential sub-pages. | EmberTribe
20 | Technical | XML Sitemap Update | Rebuild sitemap to prioritize new informational hub pages, exclude /product/ duplicates and low-value pages. | EmberTribe
21 | Technical | Broken Internal Link Fixes (Batch 1) | Fix first batch of broken internal links identified in audit (59 total flagged). Target: 20+ resolved this month. | EmberTribe
22 | Technical | Missing Meta Descriptions (Batch 1) | Add meta descriptions to 30 pages missing them (identified in audit). Prioritize Ohio pages and top-traffic pages. | EmberTribe
23 | Technical | Multiple H1 Tag Fixes (Batch 1) | Correct pages with multiple H1 tags (19 flagged in audit). One H1 per page, keyword-aligned. | EmberTribe
24 | Technical | llms.txt / AEO Foundation File | Create and publish llms.txt file. Establishes AI/AEO foundation (currently zero — identified in audit). | EmberTribe
25 | On-Page | /courses-by-state/oh/ Optimization | Rewrite H1, H2 structure, meta title, meta description. Expand intro copy. Add internal links to credential sub-pages. | EmberTribe
26 | On-Page | /product-category/oh/ Optimization | Update title tag, meta description, add canonical pointing to Ohio hub. Ensure it doesn't compete with hub for same keywords. | EmberTribe
27 | On-Page | /ohio-faq/ Optimization | Optimize FAQ page. Consolidate FAQ content into Ohio hub page strategy. Update internal linking. | EmberTribe
28 | On-Page | /ohio-cdca-preliminary-phase-i/ Optimization | Rewrite title tag (keyword: 'Ohio CDCA Preliminary CEUs'), H1, meta description. Add informational context + internal links. | EmberTribe
29 | On-Page | /ohio-cdca-phase-ii/ Optimization | Rewrite title tag (keyword: 'Ohio CDCA Renewable CEUs'), H1, meta description. Add credential context + internal links. | EmberTribe
30 | On-Page | /ohio-lcdc-ii-iii-and-licdc/ Optimization | Rewrite title, H1, meta. Add LCDC II/III/LICDC requirement context, hour tables, internal links. | EmberTribe
31 | On-Page | /ohio-lcdc-ii-iii-and-licdc-for-those-holding-a-cdca/ Optimization | Rewrite title, H1, meta. Target 'Ohio LCDC from CDCA' keyword cluster. | EmberTribe
32 | On-Page | Homepage Internal Linking Update | Add strategic internal links from homepage to Ohio hub and top-priority state pages. | EmberTribe
33 | On-Page | Texas Hub Page On-Page Refresh | Update title tag, H1, meta on existing Texas hub. CEU Matrix already ranks in top 10 for LCDC TX — protect and improve. | EmberTribe
34 | On-Page | New Articles Internal Linking Pass | After articles publish, add internal links from new content to relevant course/product pages to pass authority. | EmberTribe
35 | Page Build | Ohio Unified Informational Hub Page | New 3,000+ word Ohio informational page. H1: 'Ohio Substance Abuse Certification.' Includes all credential tables, OCDP #50-19236, FAQs, anchor nav, internal links to course pages. | EmberTribe
36 | Page Build | CDCA Preliminary Credential Page | New informational page targeting 'Ohio CDCA Preliminary certification requirements.' Requirement tables, hour breakdowns, FAQ schema, links to purchase. | EmberTribe
37 | Page Build | CDCA Renewable Credential Page | New informational page targeting 'Ohio CDCA Renewable CEUs.' Renewal requirements, hour tables, FAQ schema, purchase links. | EmberTribe
38 | Reporting | Month 2 SEO Progress Report | Keyword ranking changes, backlinks acquired (with domain details), articles published (with URLs), technical fixes completed, traffic delta. | EmberTribe
39 | Reporting | Month 2 Strategy Call | 30–60 min call. Review Month 2 data, approve Month 3 content calendar, confirm page build topics. | Both
MONTH 3 — Rankings Move
40 | Content | 20 ClusterMagic Articles | 20 SEO-optimized articles. Topics shift toward 'how to become' guides, salary content, and criminal justice counselor angle (CASR gap). | EmberTribe
41 | Backlinks | 6 Quality Backlinks | 6 backlinks. Focus on NAADAC-adjacent and state board directory links identified in Month 1 backlink gap report. | EmberTribe
42 | Technical | Broken Internal Link Fixes (Batch 2) | Continue resolving broken internal links from audit. Target: 20+ additional resolved. | EmberTribe
43 | Technical | Duplicate Title Tag Fixes | Resolve 6 duplicate title tags identified in audit. Ensure every indexed page has a unique, keyword-targeted title. | EmberTribe
44 | Technical | FAQPage Schema — LCDC New Entrant Page | Implement FAQPage JSON-LD on LCDC II/III/LICDC 180hr new entrant credential page. | EmberTribe
45 | Technical | FAQPage Schema — LCDC from CDCA Page | Implement FAQPage JSON-LD on LCDC II/III/LICDC 110hr (from CDCA) credential page. | EmberTribe
46 | Technical | BreadcrumbList Schema — New Credential Pages | Add BreadcrumbList JSON-LD to LCDC credential pages and Texas hub. | EmberTribe
47 | Technical | Thin Content Fixes (Batch 1) | Add substantive content to highest-priority thin pages (58 flagged in audit with low text-to-HTML ratio). Target: 15+ pages improved. | EmberTribe
48 | Technical | Internal Link Density — Pages with 1 Link | Add internal links to 31 pages flagged with only 1 internal link. Improves crawlability and authority distribution. | EmberTribe
49 | Technical | Site Speed Optimization | Address site speed issues identified in audit. Focus on image compression, render-blocking resources, and Core Web Vitals. | EmberTribe
50 | Technical | WebPage Schema — Ohio Hub | Add WebPage JSON-LD schema to Ohio unified hub for enhanced SERP appearance. | EmberTribe
51 | Technical | Google Search Console — Submit New URLs | Request indexing for all new pages built in Months 2–3 via GSC URL Inspection tool. | EmberTribe
52 | On-Page | Pennsylvania Hub Page Optimization | CEU Matrix ranks #10 for 'addiction counselor certification Pennsylvania.' Update title, H1, meta, expand content. Defend + improve ranking. | EmberTribe
53 | On-Page | /ohio-20-hour-renewal-package/ Optimization | Rewrite title, H1, meta description. Add renewal requirement context and internal links. | EmberTribe
54 | On-Page | /ohio-30-hour-renewal-package/ Optimization | Rewrite title, H1, meta description. Add renewal requirement context and internal links. | EmberTribe
55 | On-Page | /ohio-40-hour-renewal-package/ Optimization | Rewrite title, H1, meta description. Add renewal requirement context and internal links. | EmberTribe
56 | On-Page | Texas LCDC Pages On-Page Optimization | CEU Matrix ranks #3 for 'online LCDC programs in Texas.' Strengthen title tags, H1s, meta on all Texas LCDC product/course pages. | EmberTribe
57 | On-Page | OCDP Provider # Citation Pass — Ohio Pages | Ensure OCDP Provider #50-19236 is cited prominently on all Ohio pages. Authority and trust signal (CASR cites their number on every Ohio page). | EmberTribe
58 | On-Page | NAADAC Provider # Citation Pass | Add NAADAC Provider #619 (issued 2005) citation to all relevant state pages and credential pages. | EmberTribe
59 | On-Page | New Month 3 Articles Internal Linking Pass | Add internal links from newly published articles to relevant course and credential pages. | EmberTribe
60 | On-Page | Criminal Justice Content On-Page Tagging | Tag and internally link all criminal justice / CJCA-related content. Build internal topical cluster around CJ counseling — CASR's blind spot. | EmberTribe
61 | On-Page | Cross-Link Ohio Hub ↔ Credential Pages | Ensure bidirectional internal linking between Ohio hub and all Ohio credential sub-pages. Hub links down; credential pages link back up. | EmberTribe
62 | Page Build | LCDC II/III/LICDC — 180hr New Entrant Page | New 3,000+ word credential page. Target: 'Ohio LCDC certification requirements new entrant.' Requirement tables, hour breakdown, FAQ schema, purchase links. | EmberTribe
63 | Page Build | LCDC II/III/LICDC — 110hr from CDCA Page | New credential page. Target: 'Ohio LCDC requirements holding CDCA.' Credential tables, pathway context, FAQ schema, purchase links. | EmberTribe
64 | Page Build | Texas Unified Informational Hub Page | New 3,000+ word Texas informational hub. H1: 'Texas Substance Abuse Certification.' All TX credential tables, TCBAP citation, FAQ schema, links to LCDC course pages. | EmberTribe
65 | Reporting | Month 3 SEO Progress Report | Ohio keyword ranking movement, backlink tally, articles indexed + early ranking data, technical fix log, traffic vs. baseline. | EmberTribe
66 | Reporting | Month 3 Strategy Call | 30–60 min call. Review Ohio ranking progress, confirm Month 4 content and page build plan, discuss extension if warranted. | Both
MONTH 4 — Ohio Complete
67 | Content | 20 ClusterMagic Articles | 20 SEO-optimized articles. Topics expand to Texas, Pennsylvania, and multi-state career content. Criminal justice angle continues. | EmberTribe
68 | Backlinks | 6 Quality Backlinks | 6 backlinks. Expand outreach to Texas and Pennsylvania board directories, substanceabusecounselor.org, and NAADAC chapter sites. | EmberTribe
69 | Technical | Redirect Strategy — /course/ URL Consolidation | If consolidating /course/ to /product/ (or vice versa), implement 301 redirects for all 4 credential pairs. Notify CEU Matrix team before execution. | EmberTribe
70 | Technical | Thin Content Fixes (Batch 2) | Continue improving thin pages from audit. Target remaining high-priority pages with low text-to-HTML ratio. | EmberTribe
71 | Technical | FAQPage Schema — Pennsylvania Hub | Implement FAQPage JSON-LD on Pennsylvania informational hub page. | EmberTribe
72 | Technical | FAQPage Schema — Texas Hub | Implement FAQPage JSON-LD on Texas informational hub page. | EmberTribe
73 | Technical | WebPage Schema — All New Hub Pages | Add WebPage + BreadcrumbList JSON-LD to all hub pages built in Months 2–4. | EmberTribe
74 | Technical | GSC Coverage Report Review | Review Google Search Console coverage report. Identify and fix any new crawl errors introduced by redirects or new pages. | EmberTribe
75 | Technical | Internal Link Audit — New Pages | Audit internal link profile on all new pages. Ensure hub pages have 10+ inbound internal links and each credential page has 5+. | EmberTribe
76 | Technical | Core Web Vitals Review | Run Lighthouse on key landing pages. Address any CWV regressions introduced during the engagement. | EmberTribe
77 | Technical | Structured Data Testing & Validation | Run all schema markup through Google's Rich Results Test. Validate no schema errors on any new or modified page. | EmberTribe
78 | Technical | Index Coverage — Force Crawl New Pages | Submit all remaining new pages for indexing via GSC. Confirm Ohio credential pages are indexed and appearing in search. | EmberTribe
79 | On-Page | Ohio Hub — Content Depth Expansion | If Ohio hub is under 4,000 words after Month 2 build, expand with exam prep tips, salary data, career path section, school pathways. Go deeper than CASR. | EmberTribe
80 | On-Page | Pennsylvania Hub Page Build Prep / Optimization | Full on-page optimization of Pennsylvania hub if built; otherwise optimize existing PA content. Target: 'addiction counselor certification Pennsylvania.' | EmberTribe
81 | On-Page | Texas Credential Pages On-Page Pass | Optimize title tags, H1s, meta on all Texas credential sub-pages. Internal link to new Texas hub. | EmberTribe
82 | On-Page | Salary & Career Content On-Page Optimization | Optimize any salary/career articles published in Months 2–3. Ensure they target featured snippets and internal link to relevant course pages. | EmberTribe
83 | On-Page | Month 4 Articles Internal Linking Pass | Add internal links from new Month 4 articles to hub pages, credential pages, and course purchase pages. | EmberTribe
84 | On-Page | Ohio Renewal Pages — Consolidation Review | Assess whether /ohio-20-hour/, /30-hour/, /40-hour/ renewal pages should be consolidated or kept separate. Implement recommendation. | EmberTribe
85 | On-Page | NAADAC #619 & Accreditation Citations — Full Site Pass | Final pass to ensure all state pages cite NAADAC Provider #619 (since 2005) and relevant state board approvals. Trust signal for E-E-A-T. | EmberTribe
86 | On-Page | Competitor Keyword Gap Review | Re-run keyword gap vs. CASR. Identify new keywords where CEU Matrix has moved up. Flag remaining opportunities for Month 5+ (if engagement continues). | EmberTribe
87 | On-Page | Cross-Link Texas Hub ↔ Texas Credential Pages | Ensure bidirectional linking between Texas hub and all Texas credential + course pages, mirroring Ohio structure. | EmberTribe
88 | On-Page | Homepage — Full On-Page Refresh | Final homepage update: title tag, meta description, H1 alignment, add links to Ohio and Texas hubs from homepage. | EmberTribe
89 | Page Build | Pennsylvania Unified Informational Hub Page | New 3,000+ word Pennsylvania hub. H1: 'Pennsylvania Substance Abuse Certification.' CADC/CAADC/CADC-R credential tables, PCBDD citation, FAQ schema, internal links to PA courses. | EmberTribe
90 | Page Build | Texas LCDC Credential Sub-Page | New credential page targeting 'Texas LCDC certification requirements.' Requirement tables, supervised hours breakdown, FAQ schema, links to TX LCDC course packages. | EmberTribe
91 | Page Build | Ohio Renewal Landing Page | Consolidated renewal page targeting 'Ohio substance abuse counselor CEU renewal.' Links to 20hr, 30hr, 40hr renewal packages. FAQ schema. Replaces thin individual renewal pages. | EmberTribe
92 | Reporting | Month 4 SEO Progress Report | Full 4-month engagement summary: total keyword movements, backlinks acquired (all domains listed), articles indexed, pages built, traffic vs. baseline, next steps. | EmberTribe
93 | Reporting | Month 4 Strategy Call — Engagement Review | 60 min review call. Present full 4-month results, discuss continuation, recommend priority states for Months 5+. | Both
ENGAGEMENT TOTALS
Articles |  | 10 (Month 1 bonus) + 20 × 3 (Months 2–4) |  |  | 70 total
Backlinks |  | 6 × 3 months (Months 2–4) |  |  | 18 total
Page Builds |  | 3 × 3 months (Months 2–4) |  |  | 9 pages total
Tech Fixes |  | 12/month × 3 months |  |  | 36 implementations
On-Page Opts |  | 12/month × 3 months |  |  | 36 optimizations
Investment |  | $4,500 × 4 months |  |  | $18,000 total