## Overview
Adriana Hoyos — SEO Implementation Workbook
Companion to: AH B2B & Franchise Digital Presence Report (decks.embertribe.com)
Prepared for: SEO strategist quoting — Jul 2026
How to use this workbook
1. Review the Phase 1 and Phase 2 task tabs — each row is a discrete, quotable line item.
2. Fill in 'Est. Hours' (yellow cells) per task based on your estimate.
3. Set your hourly rate once on the Quote Summary tab (yellow cell) — cost columns and totals calculate automatically.
4. Keyword Targets tab shows verified search-demand data (Semrush, Jul 2026) behind the Phase 2 content tasks.
5. Competitor Reference tab shows the domain-authority/backlink benchmarks referenced in the client report.
6. Access & Dependencies tab lists what needs to be granted before each phase can start — flag anything still open.
7. Excluded / Phase 3 tab documents what was deliberately left out of this quote and why — do not price it in.
Legend
Yellow fill = enter your estimate here
Tan fill = calculated subtotal, do not edit

## Quote Summary
SEO Implementation — Quote Summary
Hourly Rate ($)
Phase | Task Count | Total Hours | Total Cost
Phase 1 — Foundation
Phase 2 — B2B / Franchise Build
Grand Total
Note: Phase 3 (franchisee playbook templating) is intentionally excluded from this quote — see 'Excluded - Phase 3' tab.

## Phase 1 - Foundation
ID | Task | Page / Scope | Current State | Target State | Priority | Access Needed | Notes | Est. Hours | Est. Cost
P1-01 | Consolidate homepage H1 tags | Homepage | 28 H1 tags found (confirmed via JS-rendered DOM audit) | Single canonical H1 | Critical | CMS/dev | Confirm which templating component is injecting duplicate H1s before removing
P1-02 | Implement structured data / schema markup | Sitewide (homepage, locations, product pages) | No LocalBusiness, Organization, or Product schema found on any page reviewed | Schema deployed sitewide | Critical | CMS/dev | Prerequisite for local-pack visibility once city pages launch in Phase 2
P1-03 | Write custom meta descriptions | Homepage, /locations/, product category pages | Missing — Google auto-generates snippet text | Custom, keyword-aligned meta descriptions | High | CMS/dev + copywriting | Coordinate voice/tone with brand team (Constanza)
P1-04 | Resolve keyword cannibalization — "Design Studio" cluster | 20+ pages | 20+ pages competing for "adriana hoyos design studio," positions 2–75 | One canonical page; others redirected or canonicalized | Critical | CMS/dev + IA decision | Ties to the confirmed decision to keep the Design Studio subdomain separate
P1-05 | Resolve keyword cannibalization — dining chairs cluster | 47 URLs | "adriana hoyos dining chairs" competes across 47 separate URLs | Canonical product/category page identified and reinforced | High | CMS/dev
P1-06 | Noindex the Design Studio subdomain | adrianahoyosdesignstudio.com | Indexable, competing with furnishing-business keywords | robots.txt noindex directive applied | Medium | Subdomain hosting/DNS access | Client confirmed on 7/10/26 call this should stay separate and unindexed
P1-07 | Press backlink dofollow outreach | Architectural Digest (2 links), Robb Report (1 link) | Both nofollow — no authority passed | Dofollow requested on next placements with each publication | Medium | PR/comms relationship (not technical) | Elle Decor's existing link is already dofollow (Page AS 34) — no action needed there
P1-08 | Referring-domain decline investigation | Sitewide backlink profile | Referring domains down from ~900 (year prior) to 657 (May '26) to 578 (Jul '26) | Root causes identified; priority reclamation list built | Medium | Backlink Analytics (in hand) + outreach capacity | Trend is still declining as of this pull
Phase 1 Subtotal

## Phase 2 - B2B Build
ID | Task | Page / Scope | Current State | Target State | Priority | Access Needed | Notes | Est. Hours | Est. Cost
P2-01 | Build Trade Program / Become a Franchisee hub | New page(s) on .com | Does not exist | Staged page with context before any login wall (model: Caracole, Bernhardt) | Critical | GA/GSC access + content + dev | Primary landing page for the entire 'trade program' keyword cluster
P2-02 | Launch .us with city-based URL structure | New domain: .us | Not live | Live with subfolder structure (/us/dc, /us/austin, /us/coral-gables) | Critical | DNS/hosting + dev | Coordinate URL structure with Meta ad-account naming (marketing team)
P2-03 | Build individual location pages | Coral Gables, DC (initial 2 cities) | Single shared /locations/ page — 1 visit/month | Dedicated page per city, each with local schema | Critical | Dev + content | Template this build so it's replicable for future cities
P2-04 | Trade-program content build | Trade Program hub + supporting pages | Zero ranking keywords in this cluster | Target "interior design trade programs," "interior designer trade program," "trade programs for interior designers" | High | Content writer + SEO | See Keyword Targets tab for full cluster and volumes
P2-05 | Franchise-opportunity content build | Franchise hub page | Zero ranking keywords in this cluster | Target "furniture franchise opportunities," "furniture franchise" | Medium | Content writer + SEO | Low volume (70/mo top term) but currently uncontested past BoConcept's #3
P2-06 | Secure GA4 / GSC access and run full baseline audit | Client analytics accounts | Not yet granted | Full keyword/traffic baseline established for precise Phase 2 scoping | Critical — blocks precise scoping | Client IT / Alegria | Requested on the 7/10/26 call; still pending as of this workbook
P2-07 | Local citation / NAP consistency pass | Coral Gables + DC (and future cities) | Unverified across directories and Google Business Profile | Consistent NAP sitewide and across major directories | High | Google Business Profile admin access
Phase 2 Subtotal

## Excluded - Phase 3
Item | Description | Why it's excluded from this quote | Revisit when
Franchisee playbook templating | Turn the .us city-page structure into a repeatable template — local SEO, local schema, and a matching Meta account — for future franchisees to launch on. | There is no second franchisee yet; Sean's DC location hasn't opened. Building a 'repeatable' template before there's a second real data point to design against is scope that can't be defended if challenged. | Once the DC location is live and a second franchisee city is identified

## Keyword Targets
Keyword | Volume/mo | Intent | KD | CPC | Currently Owned By | Position | Cluster | Target Page (fill in)
interior design trade programs | 90 | Informational | 13 | 19.74 | — | — | Trade Program
interior designer trade program | 50 | Informational | 26 | 18.76 | — | — | Trade Program
interior designer trade programs | 50 | Commercial | 15 | 10.19 | Ethan Allen | #32 | Trade Program
trade programs for interior designers | 40 | Commercial | 17 | 7.65 | — | — | Trade Program
trade program for interior designers | 30 | — |  | 10.69 | — | — | Trade Program
to the trade | 210 | — |  |  | Caracole | #12 | Trade Program
into trade | 320 | — |  |  | Caracole | #39 | Trade Program
ethan allen trade program | 50 | Navigational | 14 | 4.77 | Ethan Allen | #1 | Trade Program (brand-specific benchmark)
furniture franchise opportunities | 70 | Informational, Commercial | 11 | 0 | BoConcept | #3 | Franchise Hub
furniture franchise | 50 | Informational | 16 | 2.33 | BoConcept | #6 | Franchise Hub
furniture store franchise | 20 | — |  | 2.97 | — | — | Franchise Hub
wholesale furniture companies in north carolina | 90 | Commercial | 54 | 0.84 | Bernhardt | #14 | One-off geo page (not a broad theme)
Deprioritized themes — do not target as broad campaigns
"Wholesale" (broad) | Top results are named local wholesale-furniture retailers (Knoxville Wholesale Furniture, Sam's Wholesale Patio Furniture) — real businesses, not B2B dealer-relationship intent.
"Dealer" (broad) | Broad match stems "dealer" into "deals" — top results are Black Friday/Costco furniture-discount searches. Doesn't measure a real B2B audience.

## Competitor Reference
Domain | Authority Score | Backlinks | Ref. Domains | Organic Keywords | Organic Traffic | Model
adrianahoyos.com | 27 (Good) | 37.6K | 578 | 190 | 1.6K | Baseline — this client
Caracole | 34 (Very good) | 31.1K | 974 | 2.6K | 11.1K | Trade program
BoConcept | 53 (Excellent) | 257.6K | 11.9K | 7.5K | 16.4K | Franchise
Roche Bobois | 52 (Excellent) | 1M | 7.4K | 5.6K | 44.8K | Franchise
Ethan Allen | 53 (Excellent) | 2.9M | 10K | 120.9K | 550.8K | Independent dealer / licensee
Bernhardt | 40 (Very good) | 34.1K | 4.2K | 17K | 101.5K | Trade program + dealer network
Artefacto | Not yet verified | — | — | — | — | LatAm-origin luxury peer — data pending
Source: Semrush Domain Overview, US database, Jul 15 2026

## Access & Dependencies
Item | Status | Blocks | Owner
Google Analytics 4 access | Not yet granted | Precise Phase 2 keyword/traffic targeting | Alegria (client)
Google Search Console access | Not yet granted | Precise Phase 2 keyword/traffic targeting | Alegria (client)
Semrush API units | Exhausted on EmberTribe account as of Jul '26 | Refreshed live competitive tracking | EmberTribe internal
CMS / dev platform access | Not yet confirmed | All Phase 1 technical fixes | Christopher (client)
.us domain registration / DNS | Status unknown | Phase 2 launch | Alegria / Christopher (client)
Design Studio subdomain hosting access | Status unknown | robots.txt noindex task (P1-06) | Christopher (client)
Google Business Profile admin access | Status unknown | Local citation/NAP work (P2-07) | Alegria (client)